### Garment Order Critical Path Tracker (90-Day Timeline)

Key Color Coding:

- 🔴 Red = Critical Delay

- 🟢 Green = On Time

- 🟡 Yellow = At Risk

- 🔵 Blue = Inspection Points

#### 1. Pre-Production (Days 1-30)

| Milestone | Owner | Duration | Dependencies | Inspection |
| --- | --- | --- | --- | --- |
| 1.1 Design Approval | Designer | 5 days | Buyer Brief | Buyer Sign-off |
| 1.2 Tech Pack Final | Tech Team | 3 days | Design Approved | Merchandiser Check |
| 1.3 Fitting Sample | Sampling Team | 7 days | Tech Pack | 🔵 Fit Model Review |
| 1.4 PP Sample | Factory | 10 days | Fitting Sample Approved | 🔵 QA & Buyer Approval |
| 1.5 Lab Dip Approval | Dyeing Mill | 12 days | Fabric Sourced | 🔵 Color Matching |
| 1.6 Accessories Approval | Procurement | 8 days | PP Sample OK | 🔵 Trim Quality Check |

#### 2. Production (Days 31-75)

| Milestone | Owner | Duration | Dependencies | Inspection |
| --- | --- | --- | --- | --- |
| 2.1 Fabric Knitting | Knitting Mill | 15 days | Lab Dip Approved | 🔵 GSM/Shrinkage Test |
| 2.2 Fabric Dyeing | Dyeing Mill | 10 days | Knitting Complete | 🔵 Shade Approval |
| 2.3 Cutting | Cutting Dept | 5 days | Fabric Received | 🔵 Cut Piece QC |
| 2.4 Sewing | Sewing Line | 20 days | Cutting Complete | 🔵 In-Line Inspection |
| 2.5 Printing/Embroidery | Subcontractor | 7 days | Sewing 50% Complete | 🔵 Design Alignment Check |

#### 3. Post-Production (Days 76-90)

| Milestone | Owner | Duration | Dependencies | Inspection |
| --- | --- | --- | --- | --- |
| 3.1 Finishing | Finishing Team | 5 days | Sewing Complete | 🔵 Thread Trimming |
| 3.2 Final QC | QA Team | 3 days | Finishing Done | 🔵 AQL 2.5 Audit |
| 3.3 Packing | Packing Team | 2 days | QC Passed | 🔵 Polybag/Label Check |
| 3.4 Shipping Sample | Merchandiser | 1 day | Packing Complete | Buyer Final Approval |
| 3.5 Shipment | Logistics | 2 days | All Approvals OK | Documentation Verify |

### Critical Path Reporting Tools

#### 1. Gantt Chart View

- Visual Timeline: Overlay planned vs. actual dates.

- Example:

plaintext

Copy

[Fitting Sample] 🟢 (On Time)

[Lab Dip]        🔴 (Delayed by 3 days) → Impacts Knitting Start

#### 2. Daily Tracker (Excel/ERP)

| Style # | Stage | Planned Date | Actual Date | Delay | Action Needed |
| --- | --- | --- | --- | --- | --- |
| STYLE-101 | PP Sample | 15-Nov | 18-Nov | +3 days | Expedite Buyer Feedback |
| STYLE-101 | Fabric Dyeing | 25-Nov | 22-Nov | -3 days | ✅ Ahead of Schedule |

#### 3. Alerts & Escalations

- Automated Notifications:

  - "Lab Dip approval delayed! Knitting start pushed to Dec 1."

- Escalation Matrix:

  - 48h delay → Notify Production Manager

72h delay → Notify Head of Merchandising

### Key Developer Requirements

- ERP Modules Needed:

  - Milestone Tracker: Date fields with traffic-light status (🟢/🟡/🔴).

  - Inspection Logs: Upload photos/reports (e.g., lab dip, AQL results).

  - Delay Calculator: Auto-adjusts downstream tasks if upstream is late.

- Integrations:

  - Calendar sync (Outlook/GSuite) for approvers.

  - WhatsApp/Email alerts for delays.

- Dashboards:

  - Merchandiser View: Style-wise critical path.

  - Factory View: Department-wise backlog.

### Sample Workflow Automation

mermaid

Copy

flowchart LR

A[Fitting Sample Approved?] -- Yes --> B[Start PP Sample]

B -- Delay? --> C{Notify Merchandiser}

C -->|>48h| D[Escalate to Production Head]